## COMM
Task |  |  | 2023 | [47 empty] | 2024
|  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
| 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Inheritance of Birds-5
MDR
Secure all components
Programming of COMM
Procurement
Preliminary Design Review(PDR)
EM Development
Thermal Testing
Vibration Testing
Long Range Test
End to End Test
After 30 mins COMM Test
Critical Design Review
FM Development
Thermal Testing
Vibration Testing
Long Range Test
End to End Test
After 30 mins COMM Test
Handover Satellite

## Antenna
Task | 2023 | [47 empty] | 2024
| January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Antenna Design
Antenna Simulation Test
6-way RF switch Procurement
Antenna Panel Design
Procuremment of Components
Bread Board Level Design and Testing
PDR
EM Fabrication
Functionality Test
Antanna Radiation Pattern Test
Anechoic Chamber Test
CDR
FM Fabrication
Functionality Test
Antenna Radiation Pattern Test
Anechoic Chamber Test
Thermal Vacuum Test
Assembly
Handover Satellite